## Slide 1: N-CORE: A JLab–MIT Academic Endpoint for AI-Enabled Nuclear Physics Phase I: connect one JLab/HPDF data path to MIT and demonstrate flagship AI workflow [14c Focus Area]
A 9-month project to establish a pilot MIT academic endpoint connected to JLab/HPDF workflows and demonstrate one end-to-end AI-enabled nuclear-physics workflow with measurable gains in speed, reproducibility, or scientific utility.

## Slide 2: N-CORE Team
Lead institution: MIT (Or Hen PI)
Partner institution: Jefferson Lab
  Ilya Baldin - HPDF technical Director (TBC)
  Laura Biven - Chief Data Officer (TBC)
  PI from the nuclear physics side (TBC)
Project structure
  MIT: endpoint, AI methods, workflow development, trainees
  JLab HPDF/data: data path, architecture, governance
  JLab NP: use-case selection, development, benchmark, science validation

## Slide 3: Project Overview
Phase-I will do three things:
  Build an MIT academic endpoint
  Shared compute, storage, software, access control
  Create one secure JLab/HPDF data path
  Approved dataset, defined access, governance
  Demonstrate one flagship AI workflow
  Run one real NP task and benchmark against baseline
Deliverable: One working endpoint + one working data path + one validated workflow

## Slide 4: HPDF Academic Node
An MIT academic endpoint is a small, persistent MIT-side environment designed to participate in a JLab workflow.
Physically / practically, it means:
  MIT compute for model development and inference
  MIT storage for approved JLab data products or subsets
  shared software environment for students and researchers
  identity / access control
  logging and reproducible execution
   The MIT endpoint is a modest pilot environment, not a new center-scale infrastructure build
It is not:
  a major hardware center
  a replacement for HPDF
  just VPN access
Why it matters: it gives MIT a standing, shared place to contribute to JLab workflows.

## Slide 5
Candidate examples
AI-assisted calibration
AI-assisted reconstruction
classification / data-quality workflow
uncertainty-aware analysis / inference on a selected dataset
Phase I requirement
The workflow must:
use an existing JLab dataset or data product
be feasible in 9 months
be benchmarkable against current practice
involve both JLab NP expertise and MIT AI development
Use case: One high-value JLab nuclear-physics workflow that is currently slow, fragmented, or labor-intensive.
Phase-I will choose one existing JLab dataset and one bottleneck task that is scientifically meaningful, feasible in 9 months, and benchmarkable against current practice.

## Slide 6
JLab dataset / data product:
  approved JLab/HPDF-to-MIT data path
  MIT academic endpoint
  AI model development / training / inference
  scientific output
  validation against current JLab workflow
Three essential pieces:
  JLab HPDF/data side: Develop approved data path
  MIT & JLab-NP side: develop and run the AI workflows, validate scientific output
Phase I Pipeline

## Slide 7: 9-months work plan
Months 0–2:
  define data-use rules and success metrics
  stand up MIT endpoint
  define HPDF/data connection plan
Months 2–4:
  enable approved data transfer / mirrored access
  load first approved data products at MIT
  set up common software / container environment
  establish baseline workflow benchmark
Months 4–6:
  implement AI-enabled method for the chosen task
  run first end-to-end tests
  compare initial outputs to baseline
  refine interfaces across MIT, HPDF/data, and NP teams
Months 6–8:
  iterate on model and workflow
  validate with JLab NP experts
  test reproducibility and usability
  document what is needed to generalize
Month 9:
  deliver working endpoint + data path + flagship workflow
  show benchmark results
  define Phase II scale-up path

## Slide 8: 9-months deliverables & metrics
Primary deliverable: A functioning MIT academic endpoint connected to a JLab/HPDF-enabled data path and used to execute one end-to-end AI-enabled nuclear-physics workflow.
Concrete deliverables
  MIT endpoint stood up and operational
  one approved JLab/HPDF-to-MIT data path in place
  one flagship workflow demonstrated end-to-end
  validated scientific output reviewed with JLab
  Phase II scale-up plan
Metrics
  Turnaround time: faster path from data to scientific output
  Reproducibility: rerunnable workflow with consistent results
  Scientific utility: improvement in calibration, reconstruction, classification, or inference
  Operational success: endpoint and data path work reliably
  Expansion potential: clear path for additional workflows in Phase II
*Initial candidate use cases include AI-assisted calibration, reconstruction, or uncertainty-aware inference on an existing JLab dataset; the final choice will be driven by scientific value and 9-month feasibility

## Slide 9: Why Now? Why AI?
Why now:
  HPDF creates a new opportunity for distributed, data-intensive workflows
  MIT has AI talent and trainees ready to engage
  Phase I can test a practical JLab–MIT model in 9 months
Why AI:
  automate calibration / reconstruction / classification
  support uncertainty-aware analysis
  shorten time from data to scientific output
  improve reproducibility

## Slide 10: Workforce Development Plan
Workforce goal - Use Phase I to create a real training path linking:
  MIT students and postdocs
  JLab HPDF/data experts
  JLab nuclear-physics scientists
Phase I activities
  1–2 co-mentored trainees
  hands-on work in AI-enabled NP workflows
  exposure to data movement, reproducibility, and scientific validation
  regular MIT–JLab technical collaboration
Why this matters: The endpoint is not only technical infrastructure. It is also the mechanism that makes JLab-connected work at MIT practical for trainees.

## Slide 11: Backup

## Slide 12: Why HPDF matters here?
HPDF is being built as a DOE Office of Science data facility for distributed, data-intensive science, led by JLab with Berkeley Lab as a partner.
It is intended to support integrated workflows across facilities, data resources, and users.
N-CORE aligns with that direction by testing one concrete university-linked workflow pattern around a JLab use case.

## Slide 13: Academic node Vs. Connecting to the HPDF
Connecting to HPDF gives access to JLab resources;
An MIT academic endpoint gives MIT a shared place to do JLab-connected work
shared environment for students and researchers
continuity across projects
reusable pattern for future workflows
The Phase I MIT endpoint is a modest pilot environment, not a new center-scale infrastructure build

## Slide 14: Academic node Vs. Connecting to the HPDF
Simple framing
HPDF gives access to JLab’s data infrastructure.
The MIT endpoint gives MIT a real place to do the work.
Why that matters
This project is about making MIT talent easier for JLab to use, not only making JLab resources easier for MIT to access.

## Slide 15: What assumptions are we making
HPDF is a JLab-led distributed data facility project, but the exact mechanisms for an MIT “academic endpoint” are not prescribed publicly and would need to be designed with JLab/HPDF leadership.
The MIT endpoint in Phase I is modest: it is a pilot environment, not a full HPDF spoke.
The flagship workflow should use approved JLab data products already suitable for a 9-month demonstration.