## Slide 1: INSTALLATION PLANNING MANPOWER SCHEDULE
Stephanie Diana Rädel
Accelerator Division

## Slide 2: INSTALLATION
Responsibility:
  Normally, TRIUMFs responsibility ends at the last valve before the experiment (for future)
  Since DL will be within the beamline, TRIUMF takes full responsibility
DL chamber will be cleaned by TRIUMF’s beamline group
Installation is done by TRIUMF’s beamlines group
  BL group leader (Doug Pretty) already requested to be part of design review, to check also with materials DL wants to use

## Slide 3: MANPOWER
Availability (manpower) of beamline group is coordinated by the “QRPP” (project planning priorities)
  Project sponsor at TRIUMF (Petr Navratil) needs to be contacted in order to “increase“ DL’s priority

## Slide 4: SCHEDULE
 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24
Optics design note |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
30 MeV program concept review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Collimator design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Collimator fabrication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Shielding design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Update the SAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Update CNSC license |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
design chamber, stands, etc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
beamline comp. fabrication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
test new taget chamber |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Beam test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca