## Slide 1: ARIEL Status, Plans, Access, Installation and Alignment
Thomas Planche and Stephanie Diana Rädel
Accelerator Division

## Slide 2: Milestones & Plans
31 MeV at low beam power
30 MeV at 10 kW
26 MeV at 1 kW
Start up in less than 30 min
8-hour continuous beam delivery
3-days continuous beam delivery
Feb. 2020
Dec. 2020
Sep. 2021
Mar. 2022
Oct. 2022
End of 2023
Upcoming ARIEL milestones:
Mid-2026: commissioning of the ARIEL tunnel
Late-2026: start of rare isotope beam production with the electron beam

## Slide 3: e-Linac timeline
Shut down period
  About 6 weeks starting first week of July to mid August
Commissioning license until November 30th 2023
  Need an operational license to deliver beam to DarkLight
June
May
September
October
November
July
August
December
January

## Slide 4: e-Linac timeline
June
May
September
October
November
July
August
December
January
From December on we are good to go to start with the installation
Until the installation start:
  As soon as the magnets/ their power supplies and hall probes are available, please ship them to TIRUMF so controls group has the chance to change them in time

## Slide 5: e-Linac timeline
June
May
September
October
November
July
August
December
January
Until the installation start:
  As soon as the magnets/ their power supplies and hall probes are available, please ship them to TIRUMF so controls group has the chance to change them in time
  Write a work request for installation
    With enough time (of notice) prep work during summer shutdown from beamlines
  Writing a new Safety Analysis Report (SAR) in order to apply for a delivery license

## Slide 6: Access

## Slide 7: e-Linac General Hall access
Electron
Linear
Accelerator
Time:
  Every week will be one day of maintenance day
  We must open the hall at the end of every day to recharge the battery (shall be changed during next shutdown)
Place:
  Hatch entrance via crane
  Maze => south east
520MeV
Cyclotron
ARIEL Targets
& Ion Sources
Maze
Hatch
(north and south)

## Slide 8: Installation & Alignment

## Slide 9: Installation and alignment will be done by Beamlines group (Doug Preddy)
Beamlines need a work request!
Will need including multiple groups since it is one job

## Slide 10: Scattering chamber
The hall has a good fiducial grid for alignment.
  Accurately placing laser for alignment.
  Transfer fiducial points to beam center.
Permanent quads will be aligned by Doug’s group and field mapped.
  This way the quads can be aligned to the field center.
  Doug can put fiducial marks on the outside (for alignment).
Target ladder needs to be out (so nothing in the beam).
Are the magnets build by Bukley in New Zeeland?
  If so, please ask for field measurements and sent them to TRIUMF.

## Slide 11: Spectrometer cabling and testing
Beamlines group (Doug Preddy) and Electrical Engineering (Dan Loui):
  Physical cabling
  operational (functional) test
  water flow
  Power supplies work
  polarity is correct and trip when interlock is pulled
  controllable; typical no readback test
Actual beam commissioning between DarkLight and beam physics group.

## Slide 12: Up-stream beamline connection
ConFlat connection
Will be established by Vacuum group (Dimo)
  Pump down and leak check
  vacuum chamber with magnets (and GEMs?) check before going in beamline

## Slide 13: Down-stream beamline connection
ConFlat connection
Will be established by Vacuum group
Instal beam-dump collimator
  south AND NORTH hatch block are needed for accessing shielding and thus dump => lift plans

## Slide 14: GEM detectors
position on spectrometer supports
  how accurate do they need to be: mm?
cable HV and HDMI cables
  Test if 15m cable are okay, otherwise back to 9m (30 ft)
    measure distance to preferred hut location
  Trigger and clock is the key
connect gas lines
  begin flushing with dry N2 : vent lines can be used
  later with Ar:CO2 75:25 : control not in the hall, bottles are up in the gas shack, controls are outside of hall due to high radiation

## Slide 15: Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca